## Page 1
Sheet1
Project Items | Item Discription | Effort | Plan Sart Date | Plan End Date
1 | Idea / Problem Solving |  | 1-30-2020 | 1-31-2020
2 | Requirement Analisis |  | 2-1-2020 | 2-5-2020
3 | Heigh Level Design |  | 2-5-2020 | 2-15-2020
4 | Low Level Design |  | 2-20-2020 | 3-1-2020
5 | Coding |  | 3-2-2020 | 3-22-2020
6 | Testing |  | 3-22-2020 | 3-27-2020
7 | Diployment
Page 1

## Page 2
Sheet1
Actual Sart Date | Actual End Date Status
2-5-2020 | 2-5-2020 completed
2-6-2020 | 2-10-2020 completed
2-10-2020 | started
Page 2